# CommonHealth — Concept Note

Integrated Longevity Research Platform — EIC Pathfinder Open 2026

| Field | Value |
| --- | --- |
| Coordinator | NGO Georgia Longevity Alliance (Reg. №404506520, ა.ა.ი.პ / non-profit) |
| Country | Georgia (Horizon Europe Associated Country since 2023) |
| Principal Investigator | Dr. Jaba Tkemaladze, MD — 150+ publications, Editor-in-Chief Longevity Horizon |
| Budget | €3.0M |
| Duration | 36 months |
| Call | EIC Pathfinder Open 2026 — deadline 12 May 2026 |
| Contact | jaba@longevity.ge · +995 555 185 161 (Tbilisi, GMT+4) |

## Vision

To transition longevity research from fragmented, descriptive, single-mechanism studies to an integrated, systems-level science of aging — enabled by privacy-preserving federated infrastructure that unifies multi-modal data streams (molecular, physiological, clinical, traditional) without centralizing sensitive data.

## Breakthrough Claim

CommonHealth delivers the first theory-to-bedside pipeline that integrates:

- A novel mechanistic theory (CDATA — Centriolar Damage Accumulation Theory of Aging)

- A falsifiable physiological biomarker (χ_Ze from Ze Vectors Theory)

- Open-source federated learning infrastructure (FCLC) meeting EU AI Act Article 22 compliance

- Wearable biomarker hardware (BioSense, TRL 1→3)

- A real-world clinical pilot (Aqtivirebuli — traditional Georgian nutritional intervention for iron-deficiency anemia)

## Work Packages

| WP | Title | Budget | Duration | TRL |
| --- | --- | --- | --- | --- |
| WP1 | FCLC — Federated learning infrastructure with DP ε ≤ 1.0, SecAgg+ | €0.6M | 12 mo | 3→5 |
| WP2 | Ze — χ_Ze biomarker validation (MPI-LEMON, Dortmund, Cuban N=196) | €0.5M | 12 mo | 2→4 |
| WP3 | CDATA — Centriolar aging Phase 0 (TTLL6, CCP1, serial BMT mice) | €0.8M | 24 mo | 2→4 |
| WP4 | BioSense — EEG+HRV wearable prototype with onboard χ_Ze | €0.6M | 18 mo | 1→3 |
| WP5 | Aqtivirebuli — Clinical pilot N=50 anemic patients, 8 weeks | €0.5M | 12 mo | 4→6 |

## Partners (current status 2026-04-17)

- ✅ Coordinator confirmed: NGO Georgia Longevity Alliance (host)

- ✅ Industry confirmed: BioViva (Liz Parrish) — CDATA WP3

- ✅ Clinical partner confirmed: Dr. Shashviashvili (Georgia) — WP5

- 🟡 EU technical partner: In recruitment (Fraunhofer IESE / KU Leuven COSIC — LoI requested)

- 🟡 HSC experimental collaborator: Prof. Hartmut Geiger (Ulm) — letter sent

## Impact Pathways

Scientific: First unified mechanistic theory + biomarker + federated data architecture for aging research. Technological: Open-source FCLC platform deployable across EU health systems; wearable BioSense prototype. Societal: Democratized longevity research; anemia intervention model scalable to 2 billion affected globally. Economic: Spinoff potential in medical devices (BioSense) and functional foods (Aqtivirebuli); Georgia positioned as Horizon Europe longevity hub.

## Honest Disclosures

- PI does not hold PhD (mitigated: 150 publications, Editor-in-Chief role, Georgia’s eligibility)

- Structural COI: PI = President of Host (full mitigation in separate COI Declaration with Supervisory Board + annual external audit)

- χ_Ze is research-stage, NOT clinically validated (Phase 1 validation in WP2)

- CDATA BHCA score: 8/27 currently (Class WEAK) — Phase 0 WP3 designed to upgrade to ≥18/27

Full Part A + Part B drafts available on request. Letters of Support required by 25 April 2026.